TANZANIA INDUSTRIAL RESEARCH AND DEVELOPMENT ORGANIZATION (TIRDO)

TIRDO Dynamic Corporate Website & Digital Services Portal

Implementation Status & Gap Analysis

Purpose: A comparison of the current implementation against the approved specification set, with prioritized recommendations to reach a production-ready, e-GA-compliant Phase I release.

Prepared by ICTT · Version 1.0 · September 2026

# 1. Executive summary

A working technical foundation for the platform has been built and is running end-to-end on a local Docker environment. The full specified stack is stood up and integrated: a responsive Next.js + TypeScript public website, a headless CMS (Strapi), PostgreSQL, Keycloak identity, MinIO object storage, OpenSearch, an Nginx reverse proxy, and a self-hosted Matomo analytics platform — all on GitHub with the beginnings of CI/CD. The public corporate website (Home, About/Governance/Management, Organization Structure, Departments, Services, News, Events, Gallery, Publications, Documents, COMSATS, T-Hub, Contact) is populated with real TIRDO content and imagery, staff sign-in runs through Keycloak, the contact form delivers email, and a first-party, ad-blocker-resistant analytics layer with a public BI dashboard is live.

In specification terms, this represents a strong first slice of the corporate-website and CMS scope plus most of the platform architecture — but it is a foundation, not yet a complete Phase I. The larger specialized modules (Technology & Innovation catalogue, Laboratory Services and the LIMS gateway, Consultancy, Training, Researcher directory and the structured Research repository) are not yet built; and several cross-cutting 'Must have' requirements — bilingual English/Kiswahili, editorial approval workflow, global search, audit logging, security hardening (WAF, admin MFA, rate limiting, VAPT), automated backups and disaster recovery, formal testing/UAT, production hosting, and the documentation set — remain outstanding. The sections below map each requirement to its current status and set out a prioritized route to a compliant production launch.

Status legend:  Done = built and working;  Partial = foundation present, work remaining;  Not started = specified but not yet implemented.

# 2. Basis of comparison

This analysis compares the running implementation against the 14 approved project documents: the Project Concept Note; Final Project Proposal; Business & Functional Requirements Specification (BFRS); Information Architecture & Detailed Sitemap; UI/UX Design Specification; Technical Architecture Specification; Database & Content-Model Specification; API & Integration Architecture Specification; Security Architecture & Cybersecurity Specification; Hosting Infrastructure & DevOps Architecture Specification; e-GA Government ICT Compliance & Governance Specification; Testing, QA & UAT Plan; Deployment, Backup, DR & Business Continuity Plan; and the Cost Estimate / BoQ / Five-Year TCO.

# 3. Functional modules — status

Mapped to the BFRS functional requirement (FR-*) groups and the Information Architecture.

| Module / capability (spec ref) | Status | What exists / what remains |
| --- | --- | --- |
| Corporate website & navigation (FR-WEB, IA) | Done | Dynamic home page, sticky mega-menu, breadcrumbs, footer, fully responsive (Next.js + TypeScript, Tailwind). |
| About TIRDO (FR-ABOUT) | Done | Mandate, vision/mission, governance, Board & Management profiles (portrait org-tree), organization structure, directorates/departments, supporting units, COMSATS. |
| Contact & enquiry management (FR-CONTACT) | Partial | Contact form stores messages and emails a recipient; unique reference numbers, status lifecycle (Received→Closed) and per-unit routing to be formalized. |
| Content Management System (FR-CMS) | Partial | Strapi headless CMS with several content types, roles and email lifecycle. Editorial approval workflow (draft→review→approve), revision history, scheduling and review dates still to be configured to spec. |
| Analytics & dashboards (FR-ANA) | Done | Matomo installed and first-party (ad-blocker-resistant) via Nginx; footer visitor counter and a public BI dashboard (Today/Month/Total, trend, top pages, countries, devices, sources). |
| News & Events (FR-NEWS, FR-EVT) | Partial | News and Events pages are live; calendar view, press releases and richer event records pending. |
| Media gallery (FR-MEDIA) | Partial | Photo gallery in place; video gallery and press releases pending; systematic image optimization to confirm. |
| Publications repository (FR-PUB) | Partial | Publications listing with downloadable PDFs; full metadata (abstract, authors, DOI, keywords, citation), faceted search and view/download tracking still needed. |
| Research & Development (FR-RD) | Partial | Basic projects exist; structured research-project records, research areas and filter/search (area, year, status, directorate, funder) not yet built. |
| Projects (FR-PRJ) | Partial | Ongoing projects shown; completed/planned states and rich cross-links (funders, outputs, technologies) pending. |
| Downloads / Resources (FR-DOC) | Partial | Documents page live; structured metadata (category, version, file type/size) to complete. |
| Online Services gateway (FR-OS) | Partial | e-Services area with Keycloak sign-in; no service integrations wired yet. |
| Authentication & accounts (FR-AUTH) | Partial | Keycloak SSO for staff and e-Services (PKCE). Public self-registration + email verification and MFA for privileged users pending. |
| Global search (FR-SRCH) | Partial | OpenSearch provisioned and a search page exists; end-to-end indexing across all content types with relevance, filters and suggestions to complete. |
| Notifications (FR-NOT) | Partial | Contact-form email only; approval/registration/review-reminder notifications and optional SMS pending. |
| APIs (FR-API) | Partial | Strapi REST/GraphQL available; versioned public API (/api/v1/...), OpenAPI/Swagger docs, gateway pattern, API auth and rate limiting to implement. |
| Researcher / Expert directory (FR-EXP) | Not started | No researcher profiles or search by specialization. |
| Technology & Innovation catalogue (FR-TECH) | Not started | No technology catalogue (readiness level, IP/commercialization status, sector filters, transfer enquiries with officer routing). |
| Laboratory Services (FR-LAB) | Not started | No laboratory directory, service catalogue, equipment/accreditation, service-request or LIMS gateway — a core specified module. |
| Consultancy (FR-CON) | Not started | No consultancy enquiry with reference numbers or staff management view. |
| Training (FR-TRN) | Not started | No training programmes or interest/registration. |
| Careers / Vacancies (FR-CAR) | Not started | Structured vacancy records with auto-archive on closing date not yet built (link/stub only). |
| Tenders / Procurement notices (FR-TEN) | Not started | Structured tender records with auto-archive not yet built (link/stub only). |
| Audit trails (FR-AUD) | Not started | No tamper-evident audit log of administrative actions. |
| External integrations — LIMS / SMS / gov shared services | Not started | Only email; LIMS gateway, SMS and government shared-service integrations pending. |

# 4. Non-functional & cross-cutting requirements — status

Mapped to the BFRS non-functional requirements (NFR-*) and the specialized architecture, security, hosting, testing and DR documents.

| Area (spec ref) | Status | What exists / what remains |
| --- | --- | --- |
| Bilingual — English & Kiswahili (FR-LANG) | Not started | Site is English-only. i18n (Strapi i18n + Next.js locale routing) and translated content required — a MoSCoW 'Must have'. |
| Security controls (NFR-SEC, Security Spec) | Partial | HTTPS-ready Nginx, Keycloak RBAC, secrets kept out of Git; missing WAF, security-header policy, admin MFA, rate limiting, input-validation review, upload malware scanning, and a pre-launch VAPT. |
| Privacy & data protection (NFR-PRIV) | Partial | Minimal data collected; purpose notices, retention periods and a data-protection review still needed. |
| Accessibility — WCAG (NFR-ACC) | Partial | Semantic HTML, alt text and keyboard-navigable menu; a formal WCAG 2.1 AA audit (automated + manual) and remediation pending. |
| Performance (NFR-PERF) | Partial | SSR/static rendering and local assets; caching/optimization, load testing and agreed targets pending. |
| Availability & monitoring (NFR-AVL) | Not started | No high availability, health monitoring or alerting. |
| Backups (NFR-BKP) | Not started | No automated backups (DB, CMS, uploads, config) or tested restores. |
| Disaster recovery & business continuity (NFR-DR) | Not started | Documented in the plan but not implemented; RTO/RPO undefined; no off-site copies. |
| Environments — dev / test / staging / prod | Partial | Local Docker (development) only; QA, staging/UAT and production environments to be stood up. |
| Production hosting (Hosting/DevOps Spec) | Not started | Runs on a local Windows Docker host; approved government hosting, load balancer, real TLS certificate and DNS pending. |
| SEO (NFR-SEO) | Partial | Readable URLs, per-page metadata and favicon; XML sitemap, robots.txt, structured data, canonical and social metadata to complete. |
| CI/CD & source control (NFR-SCM, CI/CD) | Partial | GitHub repository and branching in use; full build/test/lint/security-scan/deploy pipeline to complete. |
| Testing & UAT (Testing/QA Plan) | Not started | No formal unit/integration/functional/accessibility/security/UAT testing or requirements-traceability matrix yet. |
| Documentation deliverables | Partial | The 14 specification documents exist; admin & user manuals, deployment/security/backup guides, API docs and test/UAT reports pending. |
| Content migration & governance | Partial | Real TIRDO content and media migrated for built sections; full migration, assigned content owners and review schedules pending. |
| e-GA compliance & governance | Partial | Governance structure documented; audit trail, interoperability/integration register, traceability and standards conformance to complete. |

# 5. Technology stack alignment

The implemented stack matches the specified baseline closely. The two deviations are the CMS (Strapi in place of the baseline Directus) and the absence, so far, of a separate NestJS backend-services layer. Both are defensible — the BFRS states technology selection remains subject to architecture review — but the CMS choice should be recorded as a governance-approved variation.

| Layer | Spec baseline | Implemented | Note |
| --- | --- | --- | --- |
| Frontend | Next.js + TypeScript | Next.js 14 + TypeScript | Aligned. |
| UI / styling | Tailwind CSS | Tailwind + shadcn-style components | Aligned. |
| CMS | Directus | Strapi | Variation — both are headless CMS; record a governance-approved deviation from the baseline. |
| Backend services | NestJS | Next.js API routes / Strapi | No separate NestJS service yet; add when transactional logic / API-gateway needs arise. |
| Database | PostgreSQL | PostgreSQL 16 | Aligned. |
| Identity & access | Keycloak | Keycloak 26 | Aligned. |
| Object storage | MinIO | MinIO | Aligned. |
| Search | OpenSearch | OpenSearch 2.x | Provisioned; content indexing/search UX to complete. |
| Reverse proxy | Nginx | Nginx | Aligned (also fronts first-party analytics). |
| Containers | Docker | Docker Compose | Aligned; orchestration (Swarm/Kubernetes) for HA in production later. |
| Analytics | Matomo | Matomo 5 (self-hosted) | Aligned and operational. |
| Version control | GitHub | GitHub | Aligned. |
| CI/CD | GitHub Actions | GitHub Actions (partial) | Pipeline to complete. |

# 6. Key gaps & risks

- Bilingual delivery is absent. English/Kiswahili is a 'Must have'; retrofitting i18n after more content is authored is more costly than doing it now.

- Production readiness (security, hosting, backups, DR) is not yet in place. The specifications mandate a WAF, admin MFA, security headers, rate limiting, a pre-launch VAPT, automated backups with tested restores, and a documented DR/BC posture with defined RTO/RPO — none of which can be skipped for a government platform.

- Core service modules are outstanding. Technology catalogue, Laboratory Services + LIMS gateway, Consultancy, Training and the Researcher/Research repository are central to the platform's purpose (industrial visibility and service discovery) and remain to be built.

- Governance evidence is thin. Audit logging, a requirements-traceability matrix, an integration register, and formal testing/UAT records are required for e-GA acceptance and are not yet produced.

- The content model is narrower than specified. The CMS currently holds a handful of content types; the Database & Content-Model spec defines ~20 entity domains (with translation tables), so the model must be extended before those modules can be populated.

- Single environment. Everything runs on one local Docker host; the spec requires separate development, staging/UAT and production environments.

# 7. Recommendations — roadmap to a compliant Phase I

## 7.1 Must-have before production launch

- Stand up staging and production environments on approved government/institutional hosting; configure DNS, a real TLS certificate and HTTPS end-to-end.

- Harden security to the Security Specification: security headers, rate limiting and a WAF (e.g. Nginx/ModSecurity or an edge WAF); enable MFA for Keycloak admin/privileged accounts; formalize secrets management and upload validation/malware scanning; then commission an independent vulnerability assessment and penetration test (VAPT) before go-live.

- Implement automated backups (PostgreSQL, CMS data, MinIO uploads, configuration) with off-site copies and a tested restore; document the DR/BC plan with agreed RTO/RPO.

- Add bilingual English/Kiswahili (Strapi i18n + Next.js locale routing, language switch, translation fallbacks) — do this before large-scale content authoring.

- Configure the editorial workflow and content roles (Contributor → Editor → Approver → Publisher) with revision history, scheduling and review dates; add a tamper-evident audit log of administrative actions.

- Complete global search: index all content types in OpenSearch and finish the search UI (relevance, filters, suggestions).

- Finish the core content model in the CMS (research areas & structured projects with filters, publications metadata, structured vacancies & tenders with auto-archive, taxonomies) and migrate the remaining real content with assigned content owners.

- Add SEO essentials: generated XML sitemap, robots.txt, canonical tags, structured data and social metadata.

- Run a WCAG 2.1 AA accessibility audit and remediate; add accessibility to the test suite.

- Execute the Testing/QA plan (unit, integration, functional, performance/load, security, accessibility) and conduct UAT with business representatives; maintain the requirements-traceability matrix and produce Test & UAT reports.

- Complete the CI/CD pipeline (build, lint, tests, security scan, container build, deploy to environments) and produce the required documentation set (admin & user manuals, deployment guide, security-configuration guide, backup/recovery guide, API documentation).

- Record the Strapi-for-Directus variation (and the deferred NestJS layer) as a governance-approved architecture decision.

## 7.2 Should-have (next increment)

- Technology & Innovation catalogue with readiness/IP status, sector filters and transfer-enquiry routing to responsible officers.

- Laboratory Services module (laboratory profiles, service catalogue, equipment/accreditation, service request) and the LIMS gateway — service discovery, client login entry point, request initiation, status and report-access via controlled APIs (LIMS keeps the operational processing).

- Consultancy and Training modules with enquiry/registration, reference numbers and notifications.

- Researcher/Expert directory linked to publications, projects and technologies.

- Versioned public API (/api/v1/…) with OpenAPI/Swagger documentation and API authentication + rate limiting.

- Notification service beyond the contact form (approvals, registrations, review reminders; optional SMS).

## 7.3 Future phases

- Full LIMS integration and other institutional systems (HR, Finance) via the API layer; government shared-services integration where applicable.

- Online quotations/payments, registered-user dashboards, e-learning, digital certificates, and AI-assisted search/chatbot — each subject to separate requirements, security review and approval, as the specifications note.

# 8. Immediate next steps

A pragmatic near-term sequence that turns the current foundation into a launch candidate:

- Agree and record the scope of Phase I production (which modules ship first) and the hosting decision (hosted VM vs. institutional data centre) with ICTT/governance.

- Provision staging + production, DNS, TLS; get HTTPS and the existing site live on a real domain.

- Land the four highest-risk 'Must haves' in parallel: bilingual, security hardening + VAPT booking, automated backups + DR, and the editorial workflow + audit log.

- Extend the content model and finish global search, then migrate remaining content with owners.

- Run the formal test cycle + UAT, close critical defects, complete documentation, and obtain UAT sign-off for go-live.

Bottom line: the architecture and the public website are off to a strong, standards-aligned start — roughly the corporate-website/CMS/analytics/identity slice of Phase I. The path to acceptance now runs through production hardening (security, hosting, backups/DR), bilingual delivery, the remaining service modules, and the governance/testing/documentation evidence the e-GA framework requires.